## STATUS_438_VSAT_GIDA_PHASE_2_QU
NO. | SITENAME | MUNICIPALITY | PROVINCE | REGION | PHASE 1 ORIGINAL AIRMAC | PHASE 1 GRAFANA AIMAC | SPARE MODEM USED | PHASE 2 AIRMAC | PHASE 1 IP ADDRESS | PHASE 2 IP ADDRESS | PHASE 1 ORIGINAL AIRMAC SERIAL | PHASE 1 TRANCEIVER | PHASE 1 EAP225-outdoor s/n 1 | PHASE 1 EAP225-outdoor s/n 2 | PHASE 1 ER-605 SERIAL | PHASE 1 LAT | PHASE 1 LONG | PHASE 1 TRANCEIVER MODEL | PHASE 1 MODEM MODEL | PHASE 2 EAP225-outdoor s/n 1 | PHASE 2 ASSIGNED KAD | INSTALLATION DATE | UAT SPEEDTEST MIR DL | UAT SPEEDTEST MIR UL | MIR LATENCY | UAT SPEEDTEST CIR AP1 DL | UAT SPEEDTEST CIR AP1 UL | AP1 LATENCY | UAT SPEEDTEST CIR AP2 DL | UAT SPEEDTEST CIR AP2 UL | AP2 LATENCY | UAT TEST DATE (DICT INPUT) | LAT | LONG | 2 - 3 SITE CONTACTS | OLD EAP225 | SITE CONTACT EMAIL/SOCMED | REMARKS
1 | VSTG2-L5-0001-SAN-ANDRES-BUNDOK-BRGY | QUEZON | ATIMONAN | IV-A | 00:06:39:91:33:b7 | 00:06:39:91:33:b7 |  | 00:06:39:91:33:b7 | 10.255.181.2 |  | b520300478026 | 2211003080108 | 2234528002165 | 2234528002719 | 22344W2004644 | 13.9526 | 121.8638 | ILB3210 Single Coax | 2010 | 224B4L0005505 | JAKE | 2025-01-29 | 40.39 | 11.88 | 559 | 37.71 | 11.48 | 569 | 32.06 | 11.59 | 570 |  | 13.9528 | 121.8637 | WALTER M. CAMPEÑA (09289794932) / MA. IRISH U. ALBANO (09182199892) |  | WALTER M. CAMPEÑA - FACEBOOK / MA. IRISH U. ALBANO - FACEBOOK | DONE
2 | VSTG2-L5-0002-SAN-ISIDRO-ILAYA-BRGY | QUEZON | BUENAVISTA | IV-A | 00:06:39:91:32:c4 | 00:06:39:91:32:c4 | 00:06:39:91:98:8c | 00:06:39:91:98:8c | 10.255.181.3 |  | b520300477945 | 2211003070108 | 2234528002717 | 2234528002718 | 22344W2004635 | 13.7283 | 122.4273 | ILB3210 Single Coax | 2010 | 224B4L0005563 | JAKE | 2025-01-31 | 40.42 | 11.79 | 558 | 36.12 | 11.15 | 585 | 37.79 | 5.72 | 594 |  | 13.7328 | 122.4201 | EMMANUEL O. GAYTA (09093905306) / BERNABE A. VILLAPLANA (09637821708) |  | EMMANUEL O. GAYTA / BERNABE A. VILLAPLANA | DONE
3 | VSTG2-L5-0003-BONIFACIO-BRGY | QUEZON | BURDEOS | IV-A | 00:06:36:91:34:26 | 00:06:39:91:34:26 |  | 00:06:39:91:34:26 | 10.255.181.6 |  | b520300478063 | 2214001460108 | 2234528002720 | 2234528002708 | 22344W2004679 | 15.0208 | 121.986 | ILB3210 Single Coax | 2010 | 224B4L0005124 | JAKE | 2025-02-13 | 38.13 | 12.36 | 572 | 36.16 | 7.12 | 592 | 36.93 | 9.18 | 593 |  | 15.0381 | 121.9793 | INTONG LEODEGARIO SANTIDAD (09426862229) |  | LEODEGARIOSANTIDAD81@gmail.com | DONE
4 | VSTG2-L5-0004-MABINI-BRGY | QUEZON | BURDEOS | IV-A | 00:06:39:91:31:a4 | 00:06:39:91:31:a4 |  | 00:06:39:91:31:a4 | 10.255.181.5 |  | b520200477849 | 2211002820108 | 2234528002707 | 2234528002716 | 22344W2003591 | 15.0157 | 122.0136 | ILB3210 Single Coax | 2010 | 224B4L0005546 | JAKE | 2025-02-12 | 39 | 12.36 | 579 | 38.99 | 12.32 | 580 | 37.23 | 10.49 | 569 |  | 15.0148 | 122.0141 | 9638460126 / 09564314205 |  | ryancoronacion2023@gmail.com | DONE
5 | VSTG2-L5-0005-ALUYON-BRGY | QUEZON | BURDEOS | IV-A | 00:06:39:91:34:41 | 00:06:39:91:e7:6b |  | 00:06:39:91:e7:6b | 10.255.181.4 |  | b520300478072 | 2211003140108 | 2234528002713 | 2234528002710 | 22344W2003525 | 14.8888 | 121.9612 | ILB3210 Single Coax | 2010 | 224B4L0000365 | JAKE | 2025-02-10 | 38.27 | 12.11 | 575 | 10.58 | 11.75 | 583 | 36.81 | 10.72 | 590 |  | 14.8761 | 121.9666 | 09103535989 / 09641897898 |  | tabrae@gmail.com / FB: Ynajane Gonzales Tagara | DONE
6 | VSTG2-L5-0006-TAMIS-BRGY | QUEZON | CALAUAG | IV-A | 00:06:39:91:33:39 | 00:06:39:91:34:29 |  | 00:06:39:91:34:29 | 10.255.181.7 |  | b520300477984 | 2213003640108 | 2234528002705 | 2234528002712 | 22344W2004698 | 14.1901 | 122.2587 | ILB3210 Single Coax | 2010 | 224B4L0005506 | JAKE | 2025-01-31 | 39.2 | 11.8 | 558 | 28.45 | 11.39 | 569 | 19.68 | 9.46 | 573 |  | 14.1899 | 122.2588 | ANGEL A. GONZALES/ NELSON PARILLA (09557604674) |  | CAISPINA VELASCO PARILLA - FACEBOOK / NELSON PARILLA - FACEBOOK | DONE
7 | VSTG2-L5-0007-CAWAYANIN-ILAYA-BRGY | QUEZON | CATANAUAN | IV-A | 00:06:39:91:32:5b | 00:06:39:91:32:5b |  | 00:06:39:91:32:5b | 10.255.181.8 |  | b520200477910 | 2214001110108 | 2234528002714 | 2234528002715 | 22344W2004369 | 13.6377 | 122.3275 | ILB3210 Single Coax | 2010 | 224B4L0005616 | JAKE | 2025-01-30 | 33.18 | 11.85 | 560 | 29.07 | 11.77 | 582 | 31.19 | 11.78 | 585 |  | 13.6377 | 122.3274 | PAULA NOCUM ROSANA (09553576819) / JACKIELYN CULLA CONDE (09954235507) |  | PAULA NOCUK ROSANA - FACEBOOK / JACKIELYN CULLA CONDE | DONE
8 | VSTG2-L5-0008-NIEVA-BRGY | QUEZON | GENERAL LUNA | IV-A | 00:06:39:91:30:d5 | 00:06:39:91:30:d5 |  | 00:06:39:91:30:d5 | 10.255.181.9 |  | b520200477780 | 2214002060108 | 2234528002711 | 2234528002702 | 22344W2004720 | 13.7333 | 122.2836 | ILB3210 Single Coax | 2010 | 224B4L0005529 | JAKE | 2025-01-30 | 40.38 | 11.81 | 562 | 32.94 | 8.9 | 572 | 37.02 | 11.76 | 561 |  | 13.6998 | 122.237 | FRECHEL C. PLATA (0915903905) / JOYCE R. FABELLA (09485187736) |  | FRECHELPLATA09@gmail.com / JOYCE FABELLA - FACEBOOK | DONE
9 | VSTG2-L5-0009-CANAWAY-BRGY | QUEZON | GENERAL NAKAR | IV-A | 00:06:39:91:32:16 | 00:06:39:91:32:16 | 00:06:39:91:34:29 | 00:06:39:91:34:29 | 10.255.181.10 |  | b520200477887 | 2214001770108 | 2234528002709 | 2234528002704 | 22344W2003601 | 15.0167 | 121.5315 | ILB3210 Single Coax | 2010 | 224B4L0005588 | JAKE | 2025-02-03 | 39.16 | 11.79 | 566 | 38.12 | 11.62 | 576 | 36.82 | 11.38 | 567 |  | 15.01 | 121.5419 | EMERSON PROHIBIDO (0910258890) / BEVERLY S. PARCO (09861010745) |  | RODALYN PROHIBIDO - FACEBOOK | DONE
10 | VSTG2-L5-0010-MAHABANG-LALIM-BRGY | QUEZON | GENERAL NAKAR | IV-A | 00:06:39:91:32:58 | 00:06:39:91:32:58 | 00:06:39:91:32:9a | 00:06:39:91:32:58 | 10.255.181.11 |  | b520200477909 | 2213003700108 | 2234528002703 | 2234528002701 | 22344W2002981 | 14.7748 | 121.4856 | ILB3210 Single Coax | 2010 | 224B4L0005333 | JAKE | 2025-01-23 | 39.37 | 11.77 | 559 | 38.44 | 11.13 | 586 | 37.59 | 10.97 | 597 |  | 14.6967 | 121.5545 | JAYPEE P. PRUDENTE (09707368652) / JUANITA P. AVELLANEDA (09381848829) |  | JAYPEE PRUDENTE - FACEBOOK / JUANITA AVELLANEDA - FACEBOOK | DONE
11 | VSTG2-L5-0011-SABLANG-BRGY | QUEZON | GENERAL NAKAR | IV-A | 00:06:39:91:34:1a | 00:06:39:92:24:69 |  | 00:06:39:92:24:69 | 10.255.181.12 |  | b520300478059 | 2134002200108 | 2234528001053 | 2234528001060 | 22344W2004808 | 14.9227 | 121.5734 | ILB3210 Single Coax | 2010 | 224B4L0005774 | JAKE | 2025-01-24 | 38.19 | 11.76 | 563 | 38.11 | 10.49 | 588 | 37.47 | 11.01 | 562 |  | 14.5489 | 121.3454 | JENNIFER T. MORILLA (09853846891) / EVELYN NANALI (09853846892) |  | JENNIFER MORILLA - FACEBOOK / EVELYN NANALI - FACEBOOK | DONE
12 | VSTG2-L5-0012-SANTO-NIÑO-ILAYA-BRGY | QUEZON | LOPEZ | IV-A | 00:06:39:91:de:30 | 00:06:39:91:de:30 |  | 00:06:39:91:de:30 | 10.255.181.80 |  | b221100483543 | 2141003040108 | 2234528002977 | 2234528002142 | 22344W2004324 | 13.835 | 122.3704 | ILB3210 Single Coax | 2010 | 224B4L0005464 | JAKE | 2025-01-31 | 40.4 | 10.25 | 580 | 35.46 | 6.85 | 592 | 32.11 | 4.06 | 600 |  | 13.8074 | 122.318 | JANICE V. CAPANZANA (09093743148) / JEANELYN E. SANTOYO (09755586976) |  | JA NI CE - FACEBOOK / JEANELYN E. SANTOYO - FACEBOOK | DONE
13 | VSTG2-L5-0013-MALABAHAY-BRGY | QUEZON | MACALELON | IV-A | 00:06:39:91:35:0a | 00:06:39:91:35:0a |  | 00:06:39:91:35:0a | 10.255.181.81 | 10.255.175.194 | b520800478139 | 2141001670108 | 2234528002974 | 2234528002968 | 22344W2003491 | 13.755 | 122.2444 | ILB3210 Single Coax | 2010 | 224B4L0000376 | JAKE | 2025-01-30 | 40.37 | 11.02 | 569 | 36.32 | 9.35 | 593 | 37.98 | 10.8 | 599 |  | 13.755 | 122.2455 | RIO GLADELYN L. POCAAN (09918105280) / MARIFE T. ANDUQUE (09629301201) |  | RIO GLADELYN L. POCAAN - FACEBOOK riogladelynpocaan13@gmail.com / marifeanduque12@gmail.com | DONE
14 | VSTG2-L5-0014-LUBAYAT-BRGY | QUEZON | REAL | IV-A | 00:06:39:91:9d:ac | 00:06:39:91:9d:ac |  | 00:06:39:91:9d:ac | 10.255.181.82 |  | b520900480896 | 2141002110108 | 2234528002143 | 2234528002976 | 22344W2004980 | 14.5007 | 121.6243 | ILB3210 Single Coax | 2010 | 224B4L0005541 | JAKE | 2025-01-23 | 39.53 | 10.5 | 564 | 39.06 | 10.64 | 588 | 40.04 | 10.49 | 591 |  | 14.5032 | 121.6299 | SNOOKY D. LORA (09321031161) / ROSEMARIE R. BUENOICHO (09707654761) |  | lorasnooky87@gmail.com / RosemariePinza@gmail.com | DONE
15 | VSTG2-L5-0015-ABIAWIN-BRGY | QUEZON | Infanta | IV-A | 00:06:39:91:32:70 | 00:06:39:91:32:70 |  | 00:06:39:91:32:70 | 10.255.181.13 |  | b520200477917 | 2214000550108 | 2234528001052 | 2234528001041 | 22344W2004718 | 14.7457 | 121.6793 | ILB3210 Single Coax | 2010 | 224B4L0005578 | JAKE | 2025-01-17 | 40.27 | 10.49 | 581 | 40.07 | 3.82 | 597 | 37.79 | 4.97 | 589 |  | 14.7457 | 121.679 | CARLA V. TENA (09081777413) / RIZALITO P. CONCHADA (09127473279) |  | loveutena@gmail.com | DONE
16 | VSTG2-L5-0016-AGOS-AGOS-BRGY | QUEZON | Infanta | IV-A | 00:06:39:91:34:35 | 00:06:39:91:34:35 |  | 00:06:39:91:34:35 | 10.255.181.15 |  | b520300478068 | 2214002280108 | 2234528001054 | 2234528001042 | 22344W2002605 | 14.7345 | 121.6243 | ILB3210 Single Coax | 2010 | 224B4L0000263 | JAKE | 2025-01-19 | 40.33 | 10.68 | 572 | 39.51 | 11.05 | 589 | 36.83 | 10.6 | 595 |  | 14.7355 | 121.6236 | ARIEL AVENO (09625772770) / LEMMUEL C. MARQUEZ |  | eighaveno@gmail.com / marquezlemmuel@gmail.com | DONE
17 | VSTG2-L5-0017-ALITAS-BRGY | QUEZON | Infanta | IV-A | 00:06:39:91:32:31 | 00:06:39:91:32:31 |  | 00:06:39:91:32:31 | 10.255.181.17 |  | b520200477896 | 2214002030108 | 2234528001056 | 2234528001044 | 22344W2003828 | 14.7044 | 121.6591 | ILB3210 Single Coax | 2010 | 224B4L0004337 | JAKE | 2025-01-20 | 37.85 | 11.31 | 568 | 39.95 | 5.99 | 578 | 34.95 | 6.35 | 583 |  | 14.7045 | 121.6591 | 09708178911 / 09854068382 / 09466567317 |  |  | DONE
18 | VSTG2-L5-0018-AMOLONGIN-BRGY | QUEZON | Infanta | IV-A | 00:06:39:91:30:66 | 00:06:39:91:30:66 |  | 00:06:39:91:30:66 | 10.255.181.19 |  | b520200477743 | 2214002010108 | 2234528001047 | 2234528001046 | 22344W2002924 | 14.7128 | 121.6351 | ILB3210 Single Coax | 2010 | 224B4L0005466 | JAKE | 2025-01-22 | 34.21 | 11.68 | 581 | 38.6 | 11.19 | 598 | 39.02 | 6.35 | 593 |  | 14.7178 | 121. 636839 | JESSIE RECAHUERTA (09695624800) / EMRA P. LARKAN (09462760291) |  | USEDOIL79@gmail.com | DONE
19 | VSTG2-L5-0019-ANIBONG-BRGY | QUEZON | Infanta | IV-A | 00:06:39:91:33:5a | 00:06:39:91:33:5a |  | 00:06:39:91:33:5a | 10.255.181.20 |  | b520300477995 | 2135001680108 | 2234528001058 | 2234528001059 | 22344W2004614 | 14.7156 | 121.647 | ILB3210 Single Coax | 2010 | 224B4L0005504 | JAKE | 2025-02-01 | 40.36 | 11.82 | 558 | 36.25 | 10.96 | 593 | 35.94 | 11.29 | 585 |  | 14.7153 | 121.6468 | EMILIANO L. MIRAS (09212867408) / ADNA V. RAMOS (09467061721) |  | EMILIANO MIRAS - FACEBOOK / ADNA V. RAMOS - FACEBOOK | DONE
20 | VSTG2-L5-0020-ANTIKIN-BRGY | QUEZON | Infanta | IV-A | 00:06:39:91:93:94 | 00:06:39:91:93:94 |  | 00:06:39:91:93:94 | 10.255.181.21 |  | b220800480268 | 2214000640108 | 2234528000735 | 2234528001051 | 2235285000429 | 14.7326 | 121.67 | ILB3210 Single Coax | 2010 | 224B4L0005468 | JAKE | 2025-01-23 | 39.72 | 11.79 | 567 | 39.47 | 6.3 | 574 | 39.25 | 11.76 | 565 |  | 14.7323 | 121.67 | RENIEL J. BECHAYDA (09109865778) / NELIN B. BERZUELA / (09463064501) |  | renielbechayda2002@gmail.com / BEBARLIN@yahoo.com | DONE
21 | VSTG2-L5-0021-BACONG-BRGY | QUEZON | Infanta | IV-A | 00:06:39:91:31:68 | 00:06:39:91:31:68 |  | 00:06:39:91:31:68 | 10.255.181.22 |  | b520200477829 | 2214001440108 | 2234528000734 | 2234528000740 | 2235285001001 | 14.7178 | 121.6513 | ILB3210 Single Coax | 2010 | 224B4L0002555 | JAKE | 2025-01-22 | 40.62 | 11.76 | 561 | 36.11 | 11.82 | 564 | 40.05 | 11.8 | 569 |  | 14.7179 | 121.6511 | MARIDEL M ASTOREZA (09388902121) / JULIETA P. MORADA (09516389335) |  | Em-em Nielneilnav - FACEBOOK maridel.astoveza29202018@gmail.com / JULIETA MORADA - FACEBOOK | DONE
22 | VSTG2-L5-0022-BALOBO-BRGY | QUEZON | Infanta | IV-A | 00:06:39:91:93:8b | 00:06:39:91:93:8b |  | 00:06:39:91:93:8b | 10.255.181.23 |  | b220800480265 | 2134004710108 | 2234528000722 | 2234528000731 | 2235285000746 | 14.7131 | 121.6631 | ILB3210 Single Coax | 2010 | 224B4L0002556 | JAKE | 2025-01-22 | 38.71 | 12.3 | 582 | 39.01 | 11.44 | 585 | 36.63 | 11.44 | 585 |  | 14.7129 | 121.6631 | MILDRED VALENZUELA (09995570308) / KHYLLA SHYNNE TUSTEZA (09218488736) |  | mhelvalenzuela2018@gmail.com / khyllatusteza@gmail.com | DONE
23 | VSTG2-L5-0023-BANUGAO-BRGY | QUEZON | Infanta | IV-A | 00:06:39:91:30:e4 | 00:06:39:91:30:e4 |  | 00:06:39:91:30:e4 | 10.255.181.25 |  | b520200477785 | 2211002670108 | 2234528000723 | 2234528000737 | 2235285000342 | 14.7468 | 121.6201 | ILB3210 Single Coax | 2010 | 224B4L0002562 | JAKE | 2025-01-22 | 39.93 | 11.09 | 579 | 39.46 | 3.37 | 581 | 39.21 | 7.26 | 578 |  | 14.7466 | 121.6204 | 09512356711 / 09512356929 |  |  | DONE
24 | VSTG2-L5-0024-BATICAN-BRGY | QUEZON | Infanta | IV-A | 00:06:39:91:30:f3 | 00:06:39:91:30:f3 |  | 00:06:39:91:30:f3 | 10.255.181.27 |  | b520200477790 | 2211003190108 | 2234528000729 | 2234528000724 | 2235285000070 | 14.7267 | 121.636 | ILB3210 Single Coax | 2010 | 224B4L0002557 | JAKE | 2025-01-19 | 40.21 | 11.49 | 576 | 37.13 | 9.32 | 585 | 38.91 | 8.25 | 587 |  | 14.726 | 121.6358 | MYRNA DY CHAVEZ (09636839547) / REGIE ANTOY (09077309291) |  | DY MYRNA CHAVEZ - FACEBOOK / REGS JIMENEZ ANTOY - FACEBOOK | DONE
25 | VSTG2-L5-0025-BINONOAN-BRGY | QUEZON | Infanta | IV-A | 00:06:39:91:2d:42 | 00:06:39:91:2d:42 |  | 00:06:39:91:2d:42 | 10.255.181.28 |  | b220700477475 | 2211003400108 | 2234528000726 | 2234528000733 | 2235285000083 | 14.7094 | 121.6364 | ILB3210 Single Coax | 2010 | 224B4L0002595 | JAKE | 2025-01-23 | 40.38 | 11.74 | 550 | 38.51 | 8.28 | 590 | 35.69 | 7.06 | 564 |  | 14.7273 | 121.6527 | 09098867126 / ELMER MORTIZ (09297343564) |  | AUGUSTO ERAMISTA GONZALES - FACEBOOK | DONE
26 | VSTG2-L5-0026-BINULASAN-BRGY | QUEZON | Infanta | IV-A | 00:06:39:91:34:53 | 00:06:39:91:34:53 | 00:06:39:94:52:ea | 00:06:39:94:52:ea | 10.255.181.88 |  | b520300478078 | 2211002980108 | 2234528002402 | 2234528002401 | 2235285000301 | 14.735 | 121.6939 | ILB3210 Single Coax | 2010 | 224B4L0002753 | JAKE | 2025-01-18 | 40.34 | 10.25 | 583 | 30.25 | 11.29 | 583 | 29.47 | 10.3 | 584 |  | 14.7342 | 121.6934 | RICO T. REVELLAME (09385273407) / NICO G. PENAMANTE (09670165863) |  | NiloPenamante@gmail.com | DONE
27 | VSTG2-L5-0027-BOBOIN-BRGY | QUEZON | Infanta | IV-A | 00:06:39:91:33:12 | 00:06:39:91:33:12 | 00:06:39:94:28:1c | 00:06:39:94:28:1c | 10.255.181.34 |  | b520300477971 | 2214000040108 | 2234528002409 | 2234528002407 | 2235285000214 | 14.7599 | 121.6588 | ILB3210 Single Coax | 2010 | 224B4L0001146 | JAKE | 2025-01-16 | 40.42 | 11.08 | 585 | 39.02 | 2.53 | 576 | 39.9 | 2.38 | 585 |  | 14.7602 | 121.6589 | 09760226537 / 09182852030 / 09859148334 |  |  | DONE
28 | VSTG2-L5-0028-CATAMBUNGAN-BRGY | QUEZON | Infanta | IV-A | 00:06:39:91:32:d6 | 00:06:39:91:32:d6 |  | 00:06:39:91:32:d6 | 10.255.181.35 |  | b520300477951 | 2214000830108 | 2234528002410 | 2234528002413 | 2235285000045 | 14.7598 | 121.6501 | ILB3210 Single Coax | 2010 | 224B4L0002522 | JAKE | 2025-01-16 | 40.38 | 10.98 | 567 | 38.61 | 2.93 | 572 | 40.27 | 2.14 | 577 |  | 14.7569 | 121.6464 | 09291795187 / 09093107976 |  | JOSHUE JAY NOLLEDO - FACEBOOK / RONILO GARIBAY - FACEBOOK | DONE
29 | VSTG2-L5-0029-CAWAYNIN-BRGY | QUEZON | Infanta | IV-A | 00:06:39:91:32:e5 | 00:06:39:91:32:e5 |  | 00:06:39:91:32:e5 | 10.255.181.36 |  | b520300477956 | 2214001790108 | 2234528002706 | 2234528002415 | 2235285000209 | 14.7235 | 121.6619 | ILB3210 Single Coax | 2010 | 224B4L0002546 | JAKE | 2025-01-23 | 38.8 | 11.76 | 564 | 37.97 | 11.76 | 570 | 11.95 | 1.08 | 580 |  | 14.7234 | 121.6618 | NARCIS BRYAN R. CAPANOS (09300959031) / RICANTE N. PAGHUNASAN (09459731263) |  | NARCIS BRYAN CAPANOS - FACEBOOK narcisbryan01@gmail.com / RICANTE N. PAGHUNASAN - FACEBOOK | DONE
30 | VSTG2-L5-0030-COMON-BRGY | QUEZON | Infanta | IV-A | 00:06:39:91:34:02 | 00:06:39:91:34:02 |  | 00:06:39:91:34:02 | 10.255.181.37 |  | b520300478051 | 2213003970108 | 2234528002406 | 2234528001804 | 2235285000755 | 14.7384 | 121.6432 | ILB3210 Single Coax | 2010 | 224B4L0002374 | JAKE | 2025-01-20 | 40.36 | 11.79 | 560 | 38.3 | 11.7 | 593 | 39.29 | 11.29 | 597 |  | 14.7569 | 121.6464 | NOEL B. PROHIBIDO (09516612276) / CASSIDY T. VALSATARA (09300814436) |  | noelprohibido@gmail.com | DONE
31 | VSTG2-L5-0031-DINAHICAN-BRGY | QUEZON | Infanta | IV-A | 00:06:39:91:33:24 | 00:06:39:91:33:24 |  | 00:06:39:91:33:24 | 10.255.181.38 |  | b520300477977 | 2211003410108 | 2234528002417 | 2234528002416 | 2235285000509 | 14.6952 | 121.7199 | ILB3210 Single Coax | 2010 | 224B4L0002563 | JAKE | 2025-01-22 | 40.35 | 11.82 | 583 | 39.03 | 8.31 | 588 | 39.94 | 9.25 | 577 |  | 14.6951 | 121.7199 | MARY ANN C. DARUCA (09517368289) / MARIZ E. BOÑON (09695235505) |  | MARY ANN DARUCA - FACEBOOK / maricbonon@gmail.com | DONE
32 | VSTG2-L5-0032-GUMIAN-BRGY | QUEZON | Infanta | IV-A | 00:06:39:91:33:ed | 00:06:39:91:33:ed |  | 00:06:39:91:33:ed | 10.255.181.41 |  | b520300478044 | 2214002350108 | 2234528001807 | 2234528002393 | 2235053001570 | 14.6999 | 121.6138 | ILB3210 Single Coax | 2010 | 224B4L0002561 | JAKE | 2025-01-21 | 39.99 | 11.88 | 562 | 9.99 | 10.47 | 573 | 11.07 | 11.2 | 576 |  | 14.6999 | 121.6138 | MELCHOR E. MERCADO JR. (09237292498) / RIZALINA C. CASTIDADES (09072810420) |  | merlchormercado3@gmail.com / rizalinacastidades@gmail.com | DONE
33 | VSTG2-L5-0033-ILOG-BRGY | QUEZON | Infanta | IV-A | 00:06:39:91:32:52 | 00:06:39:91:32:52 |  | 00:06:39:91:32:52 | 10.255.181.43 |  | b520200477907 | 2214001620108 | 2234528002390 | 2234528002394 | 2235053000595 | 14.7565 | 121.6442 | ILB3210 Single Coax | 2010 | 224B4L0002559 | JAKE | 2025-01-17 | 38.19 | 10.79 | 576 | 39.86 | 11.09 | 579 | 33.68 | 4.19 | 591 |  | 14.7492 | 121.6416 | VALENTINO ORTIZA (09300764357) / MYLA BORRXO (09291324001) |  | ortizvalentino555@gmail.com | DONE
34 | VSTG2-L5-0034-INGAS-BRGY | QUEZON | Infanta | IV-A | 00:06:39:91:32:9a | 00:06:39:91:32:9a | 00:06:39:91:32:97 | 00:06:39:91:32:9a | 10.255.181.46 |  | b520300477931 | 2214002000108 | 2234528002397 | 2234528002391 | 2235053001097 | 14.7519 | 121.6624 | ILB3210 Single Coax | 2010 | 224B4L0002545 | JAKE | 2025-01-19 | 40.31 | 11.68 | 573 | 35.82 | 11.61 | 580 | 38.01 | 10.95 | 599 |  | 14.7517 | 121.6624 | JOJIT DHINDO E. PURPURA (09480509925) / 09491243853 Ronelo C. Gucilatar(Kagawad) 09814394054 |  | almazanedmar15@gmail.com | DONE
35 | VSTG2-L5-0035-LANGGAS-BRGY | QUEZON | Infanta | IV-A | 00:06:39:91:2d:27 | 00:06:39:91:2d:27 |  | 00:06:39:91:2d:27 | 10.255.181.89 |  | b220700477466 | 2213003820108 | 2234528002386 | 2234528002398 | 2235053001519 | 14.7151 | 121.6551 | ILB3210 Single Coax | 2010 | 224B4L0002591 | JAKE | 2025-01-22 | 35.18 | 12.03 | 584 | 38.21 | 10.49 | 597 | 37.5 | 10.39 | 578 |  | 14.7129 | 121.6575 | 09426847909 / 09075004144 |  |  | DONE
36 | VSTG2-L5-0036-LIBJO-BRGY | QUEZON | Infanta | IV-A | 00:06:39:91:34:e9 | 00:06:39:91:34:e9 |  | 00:06:39:91:34:e9 | 10.255.181.48 |  | b520800478128 | 2141003260108 | 2234528001939 | 2234528001940 | 2235053000680 | 14.7525 | 121.6679 | ILB3210 Single Coax | 2010 | 224B4L0002792 | JAKE | 2025-01-20 | 40.02 | 11.72 | 545 | 36.79 | 6.46 | 562 | 35.39 | 10.49 | 588 |  | 14.7129 | 121.6575 | NEIL M. DIOLATA (09385273703) / HAROLD VILLORENTE (09087990481) |  | NEIL DIOLATA - FACEBOOK / HAROLD VILLORENTE - FACEBOOK | DONE
37 | VSTG2-L5-0037-LUAL-BRGY | QUEZON | Infanta | IV-A | 00:06:39:91:bd:19 | 00:06:39:91:bd:19 |  | 00:06:39:91:bd:19 | 10.255.181.50 |  | b221000482971 | 2141004240108 | 2234528001926 | 2234528002363 | 2235053000523 | 14.7306 | 121.6501 | ILB3210 Single Coax | 2010 | 224B4L0002558 | JAKE | 2025-01-27 | 40.19 | 10.51 | 559 | 39.1 | 11.06 | 596 | 40.33 | 11.39 | 588 |  | 14.7255 | 121.6512 | CIELO REJANE R. AMIRA (09303993031) / LONOMY P. MERCADO (09073175904) |  | cielorejaneritud@gmail.com / lonomymercado@gmail.com | DONE
38 | VSTG2-L5-0038-MAGSAYSAY-BRGY | QUEZON | Infanta | IV-A | 00:06:39:92:29:b8 | 00:06:39:92:29:b8 |  | 00:06:39:92:29:b8 | 10.255.181.52 |  | b221800486605 | 2141003840108 | 2234528001938 | 2234528002375 | 2235053001150 | 14.7069 | 121.5992 | ILB3210 Single Coax | 2010 | 224B4L0002547 | JAKE | 2025-02-15 | 38.79 | 11.7 | 571 | 38.82 | 11.66 | 597 | 37.03 | 10.49 | 592 |  | 14.7068 | 121.599 | ULPIANO M. CRISOSTOMO JR (09103442133) / BAYANI ORDINARIO (09465823749) |  | ULPIANO M. CRISOSTOMO JR - FACEBOOK / BAYANI ORDINARIO - FACEBOOK | DONE
39 | VSTG2-L5-0039-MAYPULOT-BRGY | QUEZON | Infanta | IV-A | 00:06:39:91:bc:ef | 00:06:39:91:bc:ef |  | 00:06:39:91:bc:ef | 10.255.181.53 |  | b221000482957 | 2141002200108 | 2234528001932 | 2234528001923 | 2235053001180 | 14.7064 | 121.6163 | ILB3210 Single Coax | 2010 | 224B4L0002768 | JAKE | 2025-01-22 | 39.82 | 11.84 | 576 | 39.07 | 7.84 | 596 | 39.33 | 8.58 | 589 |  | 14.7269 | 121.6643 | THELMA A. RUZOL (09396540129) / ADELO A. RAMIREZ (09855624638) |  | THELMA RUZON - FACEBOOK / ADELO PNOG RAMIREZ - FACEBOOK | DONE
40 | VSTG2-L5-0040-MISWA-BRGY | QUEZON | Infanta | IV-A | 00:06:39:91:35:34 | 00:06:39:91:35:34 |  | 00:06:39:91:35:34 | 10.255.181.54 |  | b520800478153 | 2141002490108 | 2234528001921 | 2234528001934 | 2235053000538 | 14.7397 | 121.6523 | ILB3210 Single Coax | 2010 | 224B4L0000373 | JAKE | 2025-01-14 | 39.76 | 10.64 | 574 | 29.62 | 3.89 | 582 | 40.06 | 7.95 | 588 |  | 14.7396 | 121.6523 | 0985406585 / 09630486610 |  | barangaymiswa116@gmail.com | DONE
41 | VSTG2-L5-0041-PILAWAY-BRGY | QUEZON | Infanta | IV-A | 00:06:39:91:db:c9 | 00:06:39:91:db:c9 |  | 00:06:39:91:db:c9 | 10.255.181.59 | 10.255.175.182 | b221000483338 | 2141004480108 | 2234528002244 | 2234528002254 | 22344W2004820 | 14.7426 | 121.6358 | ILB3210 Single Coax | 2010 | 224B4L0000969 | JAKE | 2025-01-21 | 38.92 | 11.23 | 574 | 38.31 | 1.5 | 593 | 38.99 | 10.32 | 586 |  | 14.7432 | 121.6321 | JOMAR (09513129852) / FLORDELIZA (09077150527) |  | pilawayinfanta@gmail.com / florderlizamagsayo@gmail.com | DONE
42 | VSTG2-L5-0042-PINAGLAPATAN-BRGY | QUEZON | Infanta | IV-A | 00:06:39:91:98:08 | 00:06:39:91:98:08 | 00:06:39:93:49:50 | 00:06:39:93:49:50 | 10.255.181.60 |  | b520800480648 | 2141001700108 | 2234528002243 | 2234528002245 | 22344W2002964 | 14.7644 | 121.6519 | ILB3210 Single Coax | 2010 | 224B4L0000898 | JAKE | 2025-01-21 | 39.9 | 11.82 | 564 | 38.34 | 11.73 | 588 | 37.33 | 10.49 | 582 |  | 14.7643 | 121.652 | 09198358969 / 093181970253 |  | ROGER MORE AUMENTADO - FACEBOOK / rheikulangsamwamwa@gmail.com | DONE
43 | VSTG2-L5-0043-POBLACION-1-BRGY | QUEZON | Infanta | IV-A | 00:06:39:91:98:26 | 00:06:39:91:98:26 | 00:06:39:95:81:73 | 00:06:39:95:81:73 | 10.255.181.61 |  | b520800480658 | 2141002590108 | 2234528002347 | 2234528002961 | 22344W2004684 | 14.7434 | 121.6498 | ILB3210 Single Coax | 2010 | 224B4L0000524 | JAKE | 2025-01-14 | 39.63 | 11.91 | 576 | 35.18 | 10.71 | 594 | 39.62 | 12.11 | 582 |  | 14.7434 | 121.6498 | 09204181859 / 09292833427 |  | mariblessprohibido@gmail.com / poblacionuno2020SB@gmail.com | DONE
44 | VSTG2-L5-0044-POBLACION-38-BRGY | QUEZON | Infanta | IV-A | 00:06:39:91:34:d7 | 00:06:39:91:34:d7 |  | 00:06:39:91:34:d7 | 10.255.181.62 |  | b520800478122 | 2141003490108 | 2234528002351 | 2234528002360 | 22344W2004697 | 14.7458 | 121.6482 | ILB3210 Single Coax | 2010 | 224B4L0000900 | JAKE | 2025-01-16 | 40.31 | 10.13 | 567 | 37.71 | 10.47 | 598 | 36.94 | 4.93 | 591 |  | 14.7453 | 121.6499 | MYLA E. MERAÑA (09463241287) / ROWELL N. POTESTADES (096778548) |  | EVANGELISTA MERANA - FACEBOOK / ROWELL N. POTESTADES - FACEBOOK | DONE
45 | VSTG2-L5-0045-POBLACION-39-BRGY | QUEZON | Infanta | IV-A | 00:06:39:91:dc:d1 | 00:06:39:91:dc:d1 |  | 00:06:39:91:dc:d1 | 10.255.176.162 |  | b221000483426 | 2141004220108 | 2234528002970 | 2234528002349 | 22344W2004850 | 14.7452 | 121.6517 | ILB3210 Single Coax | 2010 | 224B4L0000882 | JAKE | 2025-01-15 | 39.83 | 11.09 | 574 | 39.45 | 8.36 | 598 | 39.56 | 10.7 | 596 |  | 14.7453 | 121. 651703 | EDNA M RUANTO (09461166396) / ROMELO C. SOLLESTRE (09081498146) |  | EDNA MITRA MESICA RUANTO - FACEBOOK / ROMELO SOLLESTRE - FACEBOOK | DONE
46 | VSTG2-L5-0046-BANTILAN-BRGY | QUEZON | Infanta | IV-A | 00:06:39:91:32:3a | 00:06:39:91:32:3a |  | 00:06:39:91:32:3a | 10.255.181.24 |  | b520200477899 | 2213003920108 | 2234528000725 | 2234528001043 | 2235285000735 | 14.7522 | 121.6494 | ILB3210 Single Coax | 2010 | 224B4L0005950 | JAKE | 2025-01-16 | 36.7 | 10.99 | 582 | 39.29 | 10.96 | 594 | 37.16 | 5.88 | 593 |  | 14.7453 | 121.6487 | JOSE S. RAMOS (09103622085) / ZHARLENE GRACE M. ABUSTAN (09197422552) |  | btpobbantilan@gmail.com | DONE
47 | VSTG2-L5-0047-PULO-BRGY | QUEZON | Infanta | IV-A | 00:06:39:92:1a:15 | 00:06:39:92:1a:15 | 00:06:39:91:34:35 | 00:06:39:91:34:35 | 10.255.176.163 |  | b221500485854 | 2141003820108 | 2234528002346 | 2234528002359 | 22344W2004824 | 14.715 | 121.634 | ILB3210 Single Coax | 2010 | 224B4L0005770 | JAKE | 2025-01-26 | 37.27 | 12.26 | 559 | 39.91 | 11.72 | 591 | 39.87 | 11.26 | 583 |  | 14.7193 | 121.6329 | MERLA B. CRISOSTOMO (09638567936) |  | bebotresplandor@gmail.com | DONE
48 | VSTG2-L5-0048-SILANGAN-BRGY | QUEZON | Infanta | IV-A | 00:06:39:91:db:f0 | 00:06:39:91:db:f0 |  | 00:06:39:91:db:f0 | 10.255.181.75 |  | b221000483351 | 2141004310108 | 2234528002980 | 2234528002966 | 22344W2004810 | 14.7411 | 121.6688 | ILB3210 Single Coax | 2010 | 224B4L0000558 | JAKE | 2025-02-03 | 39.15 | 10.76 | 574 | 38.05 | 6.5 | 585 | 37.73 | 9.96 | 598 |  | 14.7411 | 121.6689 | JEANY SOLIVA (09398297855) / MARVEN MURALLA (09391290715) |  | SILANGAN INFANTA - FACEBOOK / infantasilangan5@gmail.com | DONE
49 | VSTG2-L5-0049-TONGOHIN-BRGY | QUEZON | Infanta | IV-A | 00:06:39:91:db:cf | 00:06:39:91:db:cf |  | 00:06:39:91:db:cf | 10.255.181.76 |  | b221000483340 | 2141002470108 | 2234528002151 | 2234528002152 | 22344W2004627 | 14.7457 | 121.6791 | ILB3210 Single Coax | 2010 | 224B4L0005779 | JAKE | 2025-01-19 | 35.09 | 10.49 | 580 | 38.89 | 11.08 | 584 | 37.44 | 8.9 | 582 |  | 14.7214 | 121.6284 | KAG. DELNOR V. SUTAREZ (0909596620) / ERNANIE AUMENTADO (09120782046) |  | DELNOR V. SUTAREZ - FACEBOOK / ERNANIE AUMENTADO - FACEBOOK | DONE
50 | VSTG2-L5-0050-TUDTURAN-BRGY | QUEZON | Infanta | IV-A | 00:06:39:91:bc:fe | 00:06:39:91:bc:fe |  | 00:06:39:91:bc:fe | 10.255.181.78 |  | b221000482962 | 2141001790108 | 2234528002969 | 2234528001929 | 22344W2004550 | 14.733 | 121.6654 | ILB3210 Single Coax | 2010 | 224B4L0000535 | JAKE | 2025-01-22 | 40.3 | 10.8 | 585 | 38.63 | 10.5 | 575 | 38.07 | 10.64 | 573 |  | 14.733 | 121.6653 | PAULENE CANIMO (09813185451) / EMILY P. PENAMORA (09384288335) |  | paulenecstrellado@gmail.com / emily p. penamora@yahoo.com | DONE
51 | VSTG2-L5-0051-SITIO-BAGUIO-OFFICE | QUEZON | Infanta | IV-A | 00:06:39:91:35:3d | 00:06:39:91:35:3d | 00:06:39:91:97:d5 | 00:06:39:91:98:53 | 10.255.181.83 |  | b520800478156 | 2141003190108 | 2234528002155 | 2234528002154 | 22344W2004764 | 14.5509 | 121.4841 | ILB3210 Single Coax | 2010 | 224B4L0000874 | JAKE | 2025-02-08 | 38.71 | 10.87 | 569 | 38.65 | 11.21 | 573 | 19.7 | 8.66 | 588 |  | 14.5507 | 121.4842 | MARLON M. MENDOYA (09761717943) / AMANDO DACILLO |  | mauieganda33@gmail.com / AMANDO DACILLO - FACEBOOK | DONE
52 | VSTG2-L5-0052-ABIAWIN-ELEM | QUEZON | Infanta | IV-A | 00:06:39:91:2d:30 | 00:06:39:91:2d:30 |  | 00:06:39:91:2d:30 | 10.255.181.14 |  | b220700477469 | 2134002960108 | 2234528001048 | 2234528001045 | 22344W2004640 | 14.7434 | 121.6781 | ILB3210 Single Coax | 2010 | 224B4L0005918 | JAKE | 2025-01-20 | 40.4 | 11.85 | 565 | 39.25 | 11.03 | 598 | 39.87 | 10.99 | 579 |  | 14.7434 | 121.6782 | MARICELL L. LEYNES (09518047389) / AINA G. MORALEDA (09993946202) |  | ainat.gonzales@deped.gov.ph | DONE
53 | VSTG2-L5-0053-AGOS-AGOS-ELEM | QUEZON | Infanta | IV-A | 00:06:39:91:30:db | 00:06:39:91:30:db | 00:06:39:95:8e:39 | 00:06:39:95:8e:39 | 10.255.181.16 | 10.255.175.184 | b520200477782 | 2214001780108 | 2234528001055 | 2234528001050 | 22344W2004235 | 14.7359 | 121.6178 | ILB3210 Single Coax | 2010 | 224B4L0000957 | JAKE | 2025-01-21 | 39.49 | 10.73 | 573 | 38.96 | 11.28 | 580 | 38.58 | 10.72 | 570 |  | 14.7356 | 121.6177 | MAILA A. MOISES (09171469137) / LENY T, CORONEL (09500749206) |  | marla.moises001@deped.gov.ph / lenytayamaracoronel@gmail.com | DONE
54 | VSTG2-L5-0054-ALITAS-ELEM | QUEZON | Infanta | IV-A | 00:06:39:91:33:9f | 00:06:39:91:33:9f |  | 00:06:39:91:33:9f | 10.255.181.87 |  | b520300478018 | 2211003380108 | 2234528001049 | 2234528001057 | 22344W2004660 | 14.7137 | 121.6577 | ILB3210 Single Coax | 2010 | 224B4L0000527 | JAKE | 2025-01-20 | 39.72 | 10.4 | 579 | 13.99 | 7.14 | 575 | 9.79 | 3.16 | 596 |  | 14.7167 | 121.6575 | 09507247981 / 09090892083 / 09489941005 |  | 108780@deped.gov.ph | DONE
55 | VSTG2-L5-0055-BANUGAO-ELEM | QUEZON | Infanta | IV-A | 00:06:39:91:30:3c | 00:06:39:91:30:3c |  | 00:06:39:91:30:3c | 10.255.181.26 |  | b520200477729 | 2214002370108 | 2234528000738 | 2234528000730 | 2235285000997 | 14.745 | 121.6262 | ILB3210 Single Coax | 2010 | 224B4L0000877 | JAKE | 2025-01-23 | 35.04 | 12.25 | 582 | 34.02 | 10.36 | 585 | 36.65 | 10.62 | 594 |  | 14.7447 | 121.6265 | 09612023621 / 09092091684 |  | banugao.elementaryschool@gmail.com / donna.alvarez@deped.gov.ph | DONE
56 | VSTG2-L5-0056-BINONOAN-ELEM | QUEZON | Infanta | IV-A | 00:06:39:91:34:14 | 00:06:39:91:34:14 | 00:06:39:90:c7:db | 00:06:39:91:34:14 | 10.255.181.29 | 10.255.181.16 | b520300478057 | 2214001240108 | 2234528000739 | 2234528000728 | 2235285000444 | 14.7093 | 121.6369 | ILB3210 Single Coax | 2010 | 224B4L0000536 | JAKE | 2025-01-28 | 38.8 | 11.87 | 562 | 13.89 | 7.85 | 588 | 36.75 | 11.51 | 573 |  | 14.7094 | 121.6367 | 09301603896 / 09090887544 |  | marladziwil@gmail.com / lermaduran@deped.gov.ph | DONE
57 | VSTG2-L5-0057-BINULASAN-IS | QUEZON | Infanta | IV-A | 00:06:39:91:33:b1 | 00:06:39:91:33:b1 |  | 00:06:39:91:33:b1 | 10.255.181.30 |  | b520300478024 | 2214000910108 | 2234528002414 | 2234528002403 | 2235285000097 | 14.732 | 121.6985 | ILB3210 Single Coax | 2010 | 224B4L0000525 | JAKE | 2025-02-07 | 38.98 | 11.41 | 577 | 38.02 | 11.63 | 564 | 37.02 | 11.35 | 567 |  | 14.7318 | 121.6981 | ARVEE JOY M. BORREO (09187733753) / RAQUEL M. SANCHEZ (09468258857) |  | arveejoy.mereya@deped.gov.ph / raquel.sanchez@deped.gov.ph | DONE
58 | VSTG2-L5-0058-DINAHICAN-ELEM | QUEZON | Infanta | IV-A | 00:06:39:91:32:46 | 00:06:39:91:32:46 | 00:06:39:90:ca:0f | 00:06:39:90:ca:0f | 10.255.181.39 |  | b520200477903 | 2211002460108 | 2234528002408 | 2234528002420 | 2235285000968 | 14.7149 | 121.712 | ILB3210 Single Coax | 2010 | 224B4L0000559 | JAKE | 2025-01-21 | 40 | 11.81 | 560 | 36.24 | 10.91 | 10.91 | 36.74 | 11.69 | 11.69 |  | 14.715 | 121.7123 | MARK ALDRIN E. ENCINA (09484832288) / DERCA C. PUSEDA (09182886846) |  | ddinahicanes@gmail.com | DONE
59 | VSTG2-L5-0059-GUMIAN-ELEM | QUEZON | Infanta | IV-A | 00:06:39:91:33:60 | 00:06:39:91:e1:36 |  | 00:06:39:91:e1:36 | 10.255.181.42 |  | b520300477997 | 2214000950108 | 2234528002382 | 2234528002381 | 2235053001103 | 14.7066 | 121.6163 | ILB3210 Single Coax | 2010 | 224B4L0000802 | JAKE | 2025-01-21 | 39.25 | 11.87 | 564 | 36.86 | 10.49 | 596 | 37.07 | 11.45 | 594 |  | 14.7064 | 121.6163 | ARNULFO M. PENAMORA (09385273872) / LAILA E. VARGAS (09495889659) |  | arnulfopenamora41@gmail.com / laila.vargas@deped.gov.ph | DONE
60 | VSTG2-L5-0060-INFANTA-CTR-ELEM | QUEZON | Infanta | IV-A | 00:06:39:91:30:30 | 00:06:39:91:30:30 | 00:06:39:95:8b:d5 | 00:06:39:95:8b:d5 | 10.255.176.169 | 10.255.176.164 | b520200477725 | 2213003950108 | 2234528002388 | 2234528002389 | 2235053000858 | 14.744 | 121.6517 | ILB3210 Single Coax | 2010 | 224B4L0005778 | JAKE | 2025-01-22 | 38.85 | 11.78 | 578 | 38.79 | 2.1 | 594 | 38.03 | 3.36 | 595 |  | 14.7453 | 121.6522 | CONTERZA CASADO (09463537624) / LERMA PEÑAMINA (09086587528) |  | conterza.alzado@deped.gov.ph / unhsreal@gmail.com | DONE
61 | VSTG2-L5-0061-INFANTA-NHS | QUEZON | Infanta | IV-A | 00:06:39:91:92:dd | 00:06:39:91:92:dd |  | 00:06:39:91:92:dd | 10.255.181.45 |  | b220700480207 | 2213003690108 | 2234528002400 | 2234528002387 | 2235053000754 | 14.743 | 121.6484 | ILB3210 Single Coax | 2010 | 224B4L0000722 | JAKE | 2025-01-16 | 40.3 | 10.9 | 555 | 39.29 | 3.88 | 3.88 | 39.55 | 5.87 | 590 |  | 14.743 | 121.6483 | 09693763600 / 09095565932 / 09206067889 |  | gilbertcandaya@gmail.com | DONE
62 | VSTG2-L5-0062-LANGGAS-NHS | QUEZON | Infanta | IV-A | 00:06:39:91:33:99 | 00:06:39:91:33:99 | 00:06:39:95:8d:19 | 00:06:39:95:8d:19 | 10.255.181.47 |  | b520300478016 | 2214000070108 | 2234528001924 | 2234528002396 | 2235053000563 | 14.7144 | 121.6588 | ILB3210 Single Coax | 2010 | 224B4L0005911 | JAKE | 2025-01-22 | 40.35 | 11.76 | 582 | 39.07 | 10.83 | 593 | 35.89 | 10.49 | 588 |  | 14.7138 | 121.6589 | YURI ANN H. ELGAR (09123616787) / ROSE ANN E. VILLANUEVA (09606500644) |  | YURI ANN HAPA - FACEBOOK yuriann.hapa@deped.gov.ph / ROSE ANN EVANGELISTA VILLANUEVA - FACEBOOK rose,evangelista@deped.gov.ph | DONE
63 | VSTG2-L5-0063-LIBJO-ELEM | QUEZON | Infanta | IV-A | 00:06:39:91:35:0d | 00:06:39:91:35:0d |  | 00:06:39:91:35:0d | 10.255.181.49 |  | b520800478140 | 2141003440108 | 2234528002364 | 2234528001937 | 2235053001334 | 14.7545 | 121.6663 | ILB3210 Single Coax | 2010 | 224B4L0000847 | JAKE | 2025-01-17 | 38.15 | 10.66 | 577 | 32.79 | 5.1 | 576 | 23.5 | 6.18 | 6.18 |  | 14.7543 | 121.6666 | CONTESSA P. CERADO (09463567924) / MARINA M. GUCILATAR (09199785190) |  | contessa.cerado@deped.gov.ph / marina.gucilatar@deped.gov.ph | DONE
64 | VSTG2-L5-0064-LUAL-ELEM | QUEZON | Infanta | IV-A | 00:06:39:91:bc:ec | 00:06:39:91:bc:ec |  | 00:06:39:91:bc:ec | 10.255.181.51 |  | b221000482956 | 2141004450108 | 2234528002365 | 2234528001933 | 2235053001512 | 14.7258 | 121.6514 | ILB3210 Single Coax | 2010 | 224B4L0000920 | JAKE | 2025-01-17 | 40.32 | 11.84 | 580 | 38.86 | 2.77 | 599 | 599 | 9.84 | 579 |  | 14.7259 | 121.6512 | 09171537204 / 09626584807 |  | hjalmar.zacarias@deped.gov.ph / hjalmar.s.zacarias - FACEBOOK | DONE
65 | VSTG2-L5-0065-PICAB-ELEM | QUEZON | Infanta | IV-A | 00:06:39:91:98:b0 | 00:06:39:91:98:b0 |  | 00:06:39:91:98:b0 | 10.255.181.58 |  | b520900480704 | 2141002330108 | 2234528002357 | 2234528002358 | 22344W2004773 | 14.7571 | 121.6509 | ILB3210 Single Coax | 2010 | 224B4L0000798 | JAKE | 2025-01-20 | 40.39 | 11.88 | 560 | 34.95 | 12.14 | 583 | 34.74 | 12.1 | 12.1 |  | 14.7533 | 121.6497 | MARY ANN L. SARMIENTO (09498761912) / OFELIA B. DELA FUENTE (09605486357) |  | mary.sarmiento003@deped.gov.ph / ofelia.delafuente001@deped.gov.ph | DONE
66 | VSTG2-L5-0066-TONGOHIN-ELEM | QUEZON | Infanta | IV-A | 00:06:39:92:22:8c | 00:06:39:92:22:8c |  | 00:06:39:92:22:8c | 10.255.181.90 |  | b221600485993 | 2141003450108 | 2234528002141 | 2234528002145 | 22344W2003415 | 14.7213 | 121.6276 | ILB3210 Single Coax | 2010 | 224B4L0000534 | JAKE | 2025-01-21 | 38.78 | 10.91 | 579 | 29.95 | 9.87 | 584 | 34.06 | 11.73 | 596 |  | 14.7208 | 121.6273 | KIMBERLY JANE VILLAPANDO (09109186203) / MARISSA PEÑAMORA |  | MIKMIK - FACEBOOK / MARISSA PEÑAMORA - FACEBOOK | DONE
67 | VSTG2-L5-0067-TONGOHIN-NHS | QUEZON | Infanta | IV-A | 00:06:39:91:9d:2e | 00:06:39:91:9d:2e |  | 00:06:39:91:9d:2e | 10.255.181.77 |  | b520900480854 | 2141002820108 | 2234528002150 | 2234528002144 | 22344W2004668 | 14.7212 | 121.6277 | ILB3210 Single Coax | 2010 | 224B4L0000545 | JAKE | 2025-01-19 | 39.77 | 11.21 | 576 | 38.94 | 5.95 | 594 | 39.02 | 6.02 | 590 |  | 14.7328 | 121.6642 | LINA S. SOBREVINAS (09634657255) / RAMON M. ABRACIA (09082743627) |  | lina.sobrevinas@deped.gov.ph / ramon.abracia@deped.gov.ph | DONE
68 | VSTG2-L5-0068-TUDTURAN-ELEM | QUEZON | Infanta | IV-A | 00:06:39:91:98:a7 | 00:06:39:91:98:a7 |  | 00:06:39:91:98:a7 | 10.255.181.79 |  | b520900480701 | 2141001880108 | 2234528002967 | 2234528002971 | 22344W2004654 | 14.733 | 121.6648 | ILB3210 Single Coax | 2010 | 224B4L0000553 | JAKE | 2025-01-22 | 39.71 | 10.61 | 581 | 37.88 | 9.33 | 595 | 37.81 | 37.81 | 600 |  | 14.733 | 121.6648 | MARIVIC L. CALINA (09303763921) / LIZA D. MANDAL (09289489608) |  | marivic.calina001@deped.gov.ph / liza.mandal@deped.gov.ph | DONE
69 | VSTG2-L5-0069-EMERGENCY-OPS-CTR | QUEZON | Infanta | IV-A | 00:06:39:91:30:96 | 00:06:39:91:30:96 | 00:06:39:91:35:4f | 00:06:39:91:35:4f | 10.255.176.167 | 10.255.175.183 | b520200477759 | 2214000900108 | 2234528002419 | 2234528002411 | 2235285001078 | 14.7433 | 121.6491 | ILB3210 Single Coax | 2010 | 224B4L0005777 | JAKE | 2025-02-06 | 39.85 | 11.28 | 581 | 37.92 | 10.99 | 585 | 40.33 | 11 | 577 |  | 14.7408 | 121.6467 | BLESILDA P. RUANTO (042-535-4466) / ARTURO S. SAGUINSIN JR. (09385650059) |  | aeromed.squadron@gmail.com / saguinsinarturo@gmail.com | DONE
70 | VSTG2-L5-0070-GOVT.-SRVC. -COMP | QUEZON | Infanta | IV-A | 00:06:39:91:34:0b | 00:06:39:91:34:0b |  | 00:06:39:91:34:0b | 10.255.176.168 |  | b520300478054 | 2214001640108 | 2234528002395 | 2234528002384 | 2235053001451 | 14.7307 | 121.6455 | ILB3210 Single Coax | 2010 | 224B4L0000721 | JAKE | 2025-01-20 | 38.44 | 11.78 | 575 | 36.55 | 10.88 | 593 | 14.64 | 6.86 | 595 |  | 14.7363 | 121.6414 | 09634902083 / DAN CASTRO (09108844059) |  | infantapeoplecounsil@gmail.com | DONE
71 | VSTG2-L5-0071-SNR-CTZN-BLDG | QUEZON | Infanta | IV-A | 00:06:39:91:9d:73 | 00:06:39:91:9d:73 |  | 00:06:39:91:9d:73 | 10.255.176.165 |  | b520900480877 | 2141002410108 | 2234528002350 | 2234528002348 | 22344W2004669 | 14.7365 | 121.6408 | ILB3210 Single Coax | 2010 | 224B4L0000862 | JAKE | 2025-01-19 | 39.25 | 11.1 | 578 | 40.03 | 10.49 | 599 | 38.37 | 6.65 | 599 |  | 14.7366 | 121.6412 | MARNELLI T. MOISES (09569230899) / ALEX R. TENA (09391249918) |  | MARNELLI TORRES MOISES - FACEBOOK / ALLEX R TENA - FACEBOOK | DONE
72 | VSTG2-L5-0072-NIYOGYUGAN-TRN-CTR | QUEZON | Infanta | IV-A | 00:06:39:91:dc:02 | 00:06:39:91:dc:02 |  | 00:06:39:91:dc:02 | 10.255.176.171 |  | b221000483357 | 2141004030108 | 2234528002356 | 2234528002242 | 22344W2003615 | 14.7364 | 121.6411 | ILB3210 Single Coax | 2010 | 224B4L0005188 | JAKE | 2025-01-15 | 38.81 | 11.41 | 581 | 34.91 | 11.27 | 584 | 39.72 | 11.19 | 600 |  | 14.7365 | 121.6409 | 9384441446 |  | ANASTACIO CORONCION ADMENTADO - FACEBOOK | DONE
73 | VSTG2-L5-0073-DINAHICAN-EXT-OFFICE | QUEZON | Infanta | IV-A | 00:06:39:91:33:93 | 00:06:39:91:33:93 |  | 00:06:39:91:33:93 | 10.255.181.40 |  | b520300478014 | 2214001970108 | 2234528002418 | 2234528001805 | 2235285001069 | 14.7109 | 121.7109 | ILB3210 Single Coax | 2010 | 224B4L0000829 | JAKE | 2025-02-05 | 39.17 | 11.81 | 556 | 37.33 | 11.67 | 561 | 36.15 | 10.89 | 566 |  | 14.4159 | 121.431 | MARY JUNE ALMACIN (09108013657) / VIRGINIA B. COMBACIA (09635105312) |  | alamcinmaryjune@gmail.com / merrionemhacia9@gmail.com | DONE
74 | VSTG2-L5-0074-MUN-FISHPORT | QUEZON | Infanta | IV-A | 00:06:39:91:bd:1f | 00:06:39:91:bd:1f |  | 00:06:39:91:bd:1f | 10.255.181.56 |  | b221000482973 | 2141004050108 | 2234528001930 | 2234528001928 | 22344W2004771 | 14.6939 | 121.7177 | ILB3210 Single Coax | 2010 | 224B4L0000849 | JAKE | 2025-01-22 | 40.44 | 11.79 | 563 | 37.1 | 11.69 | 579 | 37.6 | 11.74 | 582 |  | 14.6933 | 121.7182 | PEDRO B. COMBALIGA (096335516265) / JHOSEPH R. VILUZ (09075569113) |  | PEDIE COMBALIGA - FACEBOOK / JHOSEPH VELUZ - FACEBOOK | DONE
75 | VSTG2-L5-0075-MNAO-AND-Q1 | QUEZON | Infanta | IV-A | 00:06:39:91:9d:a0 | 00:06:39:91:9d:a0 |  | 00:06:39:91:9d:a0 | 10.255.181.55 |  | b520900480892 | 2141002520108 | 2234528001927 | 2234528001931 | 2235053001077 | 14.7466 | 121.6489 | ILB3210 Single Coax | 2010 | 224B4L0000959 | JAKE | 2025-01-17 | 39.03 | 11.41 | 577 | 15.08 | 2.47 | 595 | 18.63 | 1.15 | 600 |  | 14.7373 | 121.642 | JANNETTE O. DIMALAYAN (09182166382) / MICHEL A. JUNTEREAL (09636155173) |  | jodimacelargan@igud.gov.ph / MICHEL A. JUNTEREAL - FACEBOOK | DONE
76 | VSTG2-L5-0076-INFANTA-COM-CTR | QUEZON | Infanta | IV-A | 00:06:39:91:2c:fa | 00:06:39:91:2c:fa |  | 00:06:39:91:2c:fa | 10.255.181.44 |  | b220700477451 | 2214001410108 | 2234528002392 | 2234528002399 | 2235053000010 | 14.7475 | 121.6506 | ILB3210 Single Coax | 2010 | 224B4L0000479 | JAKE | 2025-01-16 | 38.71 | 11.22 | 584 | 38.65 | 10.87 | 597 | 39.02 | 2.25 | 595 |  | 14.7475 | 121.6505 | MADE C. CRISOSTOMO (042-535-4363) |  | lgyiccinfanta@gmail.com | DONE
77 | VSTG2-L5-0077-NEW-RHU-BLDG | QUEZON | Infanta | IV-A | 00:06:39:92:23:2b | 00:06:39:92:23:2b |  | 00:06:39:92:23:2b | 10.255.181.57 |  | b221600486046 | 2141004010108 | 2234528002241 | 2234528002255 | 2235053000234 | 14.7461 | 121.6495 | ILB3210 Single Coax | 2010 | 224B4L0005876 | JAKE | 2025-01-16 | 38.83 | 11 | 586 | 37.61 | 1.65 | 1.65 | 36.75 | 3.5 | 592 |  | 14.7429 | 121.6491 | 09657914769 / 09454929547 / 09300768502 |  | dcdchaii8234@gmail.com | DONE
78 | VSTG2-L5-0078-BINONOAN-TOURISM-SITE | QUEZON | Infanta | IV-A | 00:06:39:91:92:f2 | 00:06:39:91:92:f2 |  | 00:06:39:91:92:f2 | 10.255.176.166 |  | b220700480214 | 2213003740108 | 2234528000727 | 2234528000736 | 2235285000952 | 14.7049 | 121.6366 | ILB3210 Single Coax | 2010 | 224B4L0000475 | JAKE | 2025-01-22 | 40.29 | 11.62 | 578 | 27.44 | 11.49 | 563 | 37.99 | 11.46 | 566 |  | 14.6938 | 121.6395 | MARCIAL COTNACIO (09396448423) / EDGAR DATOS (09202260356) |  |  | DONE
79 | VSTG2-L5-0079-ALITAS-TOURISM-SITE | QUEZON | Infanta | IV-A | 00:06:39:91:32:43 | 00:06:39:91:32:43 |  | 00:06:39:91:32:43 | 10.255.181.18 |  | b520200477902 | 2211003540108 | 2234528000732 | 2234528000721 | 22344W2004769 | 14.7111 | 121.6572 | ILB3210 Single Coax | 2010 | 224B4L0000503 | JAKE | 2025-01-21 | 40.37 | 11.76 | 563 | 38.12 | 10.75 | 577 | 35.67 | 11.78 | 598 |  | 14.7025 | 121.6633 | 09812993388 / 09708177911 |  | cristelle.pujate.1 - FACEBOOK / Edwin.huplo.2024 - FACEBOOK | DONE
80 | VSTG2-L5-0080-EVACUATION-BUILDING | QUEZON | Infanta | IV-A | 00:06:39:91:e1:4b | 00:06:39:91:e1:4b |  | 00:06:39:91:e1:4b | 10.255.176.170 |  | b221400483808 | 2141003230108 | 2234528001935 | 2234528001922 | 2235053000954 | 14.7031 | 121.7147 | ILB3210 Single Coax | 2010 | 224B4L0000481 | JAKE | 2025-01-22 | 37.75 | 11.72 | 580 | 37.3 | 11.53 | 595 | 37.81 | 11.82 | 600 |  | 14.6977 | 121.7247 | 09929359787 nurse abby |  | marvinavis9@gmail.com / avislouisiana@gmail.com | DONE
[37 empty] | TOTAL SITES DONE | 80